## Master
Requirements | Version | Status | Agreed date | Priority | Estimate in Hrs
A digitizer with account in keycloak should be able login to ingestion client. | V1 | done
A digitizer must ble able to then select the directory and process assets from that directory. | V1 | done
Delete files from TUSD, temporary folder on server | V1 | done
The client has a better user interface. | V1 | done
Integrity metrics and checks | V1 | done
The system should be broken into microservices to assign different responsibilities. | V1 | done
Redesign and deploy Utils package to PyPi, updated to conform to new metadata | V1 | done
The IC should be able to verify if each TIF has a corresponding raw file and save the original names in a db | V1 | not done |  | 1.2 | 15
Delete files from workstation | V1 | not done |  | 1.3 | 5
automatically fetch the values from db based on Workstation | V1 | not done |  | 1.4 | 5
Deploy and distrube distribute Ingestion Client | V1 | not done |  | 1.5 | 10
Push everything to github | V1 | not done |  | 1.6 | 5
Testing | V1 | not done |  | 1.7 | 30
Documentation | V1 | not done |  | 1.8 | 45
autoupdate the IC application | V1 | not done |  | 2 | 15
Error tracking/logging | V1 | not done |  |  | 50
The digitiser is presented with the metadata fields with the options to select values for those fields | V1
The digitiser can save the metadata fields, these fields should apply to all files in working directory | V1
Digitser is able to the start processing which queues the data to the server and processses any incoming requests | V1
Continuous file upload. | V2 | not done |  | 4 | 50
Role-based access control for user management | V2 | not done |  |  | 25
Role based access control selecting metadata field | V2 | not done |  |  | 25
Role based access for institutions and Pipelines with different work flows | V2 | not done |  |  | 40
The server consumes a message containing an HTTP link to upload to ARS | V2 | not done |  |  | 50
Error handling if ARS is down | V2 | not done |  |  | 30
The architecture should include a health check microservice that monitors individual services. It notifies the other services when a specific service is currently down. | V2 | not done |  |  | 60
Create different pipelines for AU & Decouple Species Web & OCR to Ingestion Client. | V2 | not done |  |  | 125
Create different pipelines for DTU | V2 | not done |  |  | 1000
Adjust folder structure and work flows & metadata for seperate pipelines | V2 | not done

## Sheet1
| Ingestion Client | Version 1 |  | Khaled hrs left: 45 approx
| Work Package Overview | Keycloak integration for loging in, Stable file transfer, better UI
# | Requirements | Estimate in Hrs | Priority | Status | Version
| A digitizer with account in keycloak should be able login to ingestion client. |  |  | done | V1
| A digitizer must ble able to then select the directory and process assets from that directory. |  |  | done | V1
| The IC should be able to verify if each TIF has a corresponding raw file and save the original names in a db | 15 | 1.2 | not done | V1
| The digitiser is presented with the metadata fields with the options to select values for those fields |  |  |  | V1
| automatically fetch the values from db based on Workstation | 5 | 1.4 | not done | V1
| The digitiser can save the metadata fields, these fields should apply to all files in working directory |  |  |  | V1
| Digitser is able to the start processing which queues the data to the server and processses any incoming requests |  |  |  | V1
| autoupdate the IC application | 15 | 2 | not done | V1
| Delete files from workstation | 5 | 1.3 | not done | V1
| Delete files from TUSD, temporary folder on server |  |  | done | V1
| The client has a better user interface. |  |  | done | V1
| Integrity metrics and checks |  |  | done | V1
| Error tracking/logging | 50 |  | not done | V1
| The system should be broken into microservices to assign different responsibilities. |  |  | done | V1
| Redesign and deploy Utils package to PyPi, updated to conform to new metadata |  |  | done | V1
| Deploy and distrube distribute Ingestion Client | 10 | 1.5 | not done | V1
| Documentation | 45 | 1.8 | not done | V1
| Testing | 30 | 1.7 | not done | V1 | hrs are approx for khaled
| Push everything to github | 5 | 1.6 | not done | V1
Version 2 | coordination with Integration server, integration of AU and DTU pipelines, Role based access, error handling, health service
| Role-based access control for user management | 25 |  | not done | V2
| Role based access control selecting metadata field | 25 |  | not done | V2
| Role based access for institutions and Pipelines with different work flows | 40 |  | not done | V2
| The server consumes a message containing an HTTP link to upload to ARS | 50 |  | not done | V2
| Error handling if ARS is down | 30 |  | not done | V2
| Continuous file upload. | 50 | 4 | not done | V2
| The architecture should include a health check microservice that monitors individual services. It notifies the other services when a specific service is currently down. | 60 |  | not done | V2
| Create different pipelines for AU & Decouple Species Web & OCR to Ingestion Client. | 125 |  | not done | V2
| Create different pipelines for DTU | 1000 |  | not done | V2
| Adjust folder structure and work flows & metadata for seperate pipelines |  |  | not done | V2
Current AU adjustments
| Add automation for deleting | 4 | 1.1 | not done
| Data export to CSV | 60 |  | not done
| Include Barcode in data send to species/db, Aksel already reads the barcode | 15 |  | not done