## Main
# | Description | WP | Status | DaSSCo Agreed Date | Date Communicated to NT | NT Hours Predicted | NT Priority | NHMD Priority | Github ticket | Completed Date | Notes | ARS Version | Reason
R1.003 | Change allocated space when downloading it from ERDA into file proxy incase the asset needs more space / has parent attached to it | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15
R1.004 | Every 5 mins (configurable), synchronise with ERDA to make sure all assets are uploaded in ERDA | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15
R1.01 | Change protocol used to upload assets to the ARS from SMB to HTTPS | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | The ARS and the Data Integration Module are not located in the same local network as DeIC (which is spread over several universities across Denmark). The change in protocol was decided to be the most optimal solution for the requirements.
R1.05 | Reinitiate sync to ERDA in case of failure | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | In case some assets got error status due to some failure, they can be triggered to sync with ERDA manually
R1.06 | Upload a file to an asset over the HTTP protocol using REST API | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | We want to be able to easily add files to assets so the files then can be persisted in the ERDA. Http allows secure and standardized file upload.
R1.07 | Upload multiple files for an asset using REST API | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 | Still not working |  | Assets can potentially have multiple files belonging to them. It is more efficient to allow multiple files being uploaded at a time. It will also provide scalability.
R1.08 | Provide confirmation and integrity checks for the file upload | 1 | Completed | 2023-12-20 | [5 empty] | 2024-06-16 | There was an issue with the way integrity check was done, they never rejected the file if it was curropt but later it was corrected |  | We need to ensure that the scientific data we transfer has been correctly transferred. We do not want to persist corrupted files or files with missing parts accidentally.
R1.09 | Provide a way to delete file/folder from file proxy | 1 | Completed | 2024-02-23 | [5 empty] | 2024-05-15 | Later it was extended to be able to delete file from ERDA also, related to R3.12 |  | Closing the file shares is a needed functionality to not run out of storage space. This is needed both when we are doing processing of an asset (downloading files to hpc) and later when end users can request an asset.
R1.10 | Provide a way to get a file from file proxy | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | When doing further processing of an asset we need to have access to it and the files belonging to it. Later end users will also be given a link where they can retrieve the files.
R1.11 | Provide a way to get file info from file proxy, including integrity checks, file size etc | 1 | Completed | 2024-04-05 | [5 empty] | related to R1.8 | Initially, the functionality was that we would provide,messageintegrity(CRC), while uploading a file and ARS would be checked against the CRC of received file, but no action would be taken, then it was requested to delete the corrupt file and send a message back that file was not persisted. Date missing. |  | To check if the file was succesfuly uploaded and to help us keep track of storage space used by the fileproxy. Also helps us determine if we have correctly received the file for processing.
R1.15 | See available files in file proxy for a given asset | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | Allows us to get the URLs for files that are available in the a file share. We can then use that URL to download the files or let others download them.
R1.16 | After sync with ERDA, request to get the asset, its file, its parent assets file from ERDA | 1 | Completed | 2024-02-23 | [5 empty] | 2024-05-15 | Parent was always checked out, but optimisation was requested, where only when parent guid was filled out when creating asset then, ERDA would be connected to get parent asset. Was part of first testing iteration, notes in GitHub |  | When an asset is synced with ERDA the file share is closed . We need a way to open a share for an asset so we can access the files again.
R1.19 | Make more modular and extensible | 1 | Completed | 2024-02-20 | [5 empty] | 2024-05-15 | Partially achieved, rest dropped. Some specifics are part of other requirements listed here. |  | It is required that new solution is modularlised for easy maintanence and future development of the system
R1.20 | Be able to adjust the amount of space allocated for an asset in file proxy | 1 | Completed | 2023-12-20 | [5 empty] | 2024-05-15 |  |  | We designate the amount of space an asset has available on the file share so we know how much space we have available. If we want to add more files to an asset we need a way to update the amount of space an asset should be given.
R1.22 | Delete files from file proxy | 1 | Completed | 2024-02-23 | [5 empty] | 2024-05-15 | Related to R3.12
R1.12 | Provide status for each asset via request | 1 | In progress | 2023-12-20 |  | 16 | 1 | 1 |  |  | Bug as sometimes showing faulty information. |  | Let us know where in the ARS part of the pipeline an asset is. It allows us to see errors, succesful creation of asset/files, persist status and storage space used.
R1.13 | Sync the asset with ERDA | 1 | In progress | 2023-12-20 |  | 16 | 1 |  |  |  | ERDA accepts files in batches with up to a few minutes intervals. i think because it was also part of the SMB protocol but never got tested, the testing done by Northtech was very inadequate. Need to finish testing. After cleaning DB this bug has come back |  | Since uploading files to ERDA is not done in a single flow we need a way to verify that the files were pushed successfully. There have been several issues with ERDA connection, including issues with unstability, not checking if the connections had died off, had to put a delay to establish simultaneous connections
R1.14 | See all the assets currently being worked on, and their status | 1 | In progress | 2023-12-20 |  | 16 |  |  |  | 2024-05-15 | This would be better if we could see all assets that had an open share listed. Not just assets without the "COMPLETED"status. The endpoint has stopped working | same version after cleaning DB | Gives an overview of assets in the ARS part of the pipeline. Lets us quickly find assets that for some reason have had their progress halted.
R1.17 | Provide health status for the systems like ERDA, IDP, ARS on request | 1 | In progress | 2023-12-20 |  | 16 | 3 | 1 |  |  | Has been documented for various API end points not consolidated into 1 endpoint, file proxy and ARS health check missing. We need to test this. Moved this to low priority |  | This will allow our other running processes (ingestion client, integration server and hpc clusters), to query and receive updates on system issues and then act accordingly.
R1.18 | Solution is scalable | 1 | In progress |  |  | 3 | 3 | 2 |  | related to R1.7 | Because WP1 was done is waterfall format, we were not able to provide feedback and suggest changes like HLS upgrade for HTTP and similar. |  | This is not explicitly mentioned in WP1 but is part of the requirement, but was the core requirement of previous work and changing to HTTP as part of initial discussion, lilke other several requirements which are presumed to be part of this WP1, as this work package only specific on change of protocol
R1.21 | Https design should offer concurrency, offer optimal management of storage space | 1 | In progress | 2023-12-20 |  | 3 | 1 |  |  |  | The disk space calculation was errorneous and was not calculated automatically from Operating System, this was requested - bug exist where the calculation of diskspace is faulty |  | This requirement partially addresed the scalability and extensibility requirement
R3.02 | Provide a way to receive only selective results from the API, e.g. in case of failure to sync with ERDA. | 3 | Completed | 2024-02-20 | [5 empty] | 2024-05-15 | Part of status in WP1
R3.12 - part | Provide delete endpoints on the existing API in test suite. These test suite endpoints should be able to delete institutions, pipelines, workstations, and assets. | 3 | Completed | 2024-02-20 | [5 empty] | 2024-05-15 | Covered by WP1 for assets- we can delete share including the files in the share in fileproxy to clean up space, and also delete files in ERDA is a peculiar way just incase. when deleting a file it doesn't update the delete_file_After_sync: assuming this a way to keep track of all files that existed for an asset but bug in functionality. This works for Northtech, but not us (other than assets - which we can). |  | The aim is to facilitate automation of integration test and deployment – This is specifically to test if for example a workstation can be created, and then deleted after receiving a confirmation.
R3.13 | Provide logs for the asset service | 3 | Completed | 2024-07-23 | [5 empty] | 2024-08-15 | Requested during deployment. Needs investigation for ucloud deployment. |  | They already existed, just got them persisted outside docker
R3.14 | Provide logs for file proxy | 3 | Completed | 2024-07-23 | [5 empty] | 2024-08-15 | Requested during deployment. Needs investigation for ucloud deployment. |  | They already existed, just got them persisted outside docker
R3.01 | Provide an endpoint to view the status of assets in bulk, for all metadata fields including range based and specific values. | 3 | In progress | 2024-02-20 |  |  |  | 1 |  | 2024-09-06 | We are testing it |  | Covered by API provided for search functionality in WP5A
R3.03 | Provide a way to receive updates on events on assets and changes to the metadata that is being logged by ARS. For example, if there is a change in metadata that has been pushed to ARS for an asset, it should update the last_updated and last_updated_by and the change in the value of the metadata field in a queue so that there is an option for it to be logged for posterity. | 3 | In progress | 2024-02-20 |  | 20 |  |  |  |  | Needs testing, lars is testing
R3.04 | Provide a way to query which assets have failed to be pushed to specify or similar. | 3 | In progress | 2024-02-20 |  | 25 |  |  |  | 2024-09-06 | Needs testing - part of WP2A and metadata discussion |  | Search API from WP5A provides that, belongs in WP2A
R3.08 | Provide endpoints to update access control to institutions, collections on the existing API | 3 | In progress | 2024-02-20 |  | 10 |  |  |  |  | Documentation/swagger doesnt show how they work, or if they do what they do. Still buggy. |  | testing what is needed
R3.09 | Update API documentation of mandatory parameters and document API requests with examples. | 3 | In progress | 2024-02-20 |  | 15 |  |  |  |  | Issues with update end points and some depricated end pointsstill in the docs |  | Swagger does that, lars testing if it swagger doc has the relevant info
R3.11 | It should be possible to give role-based access to assets, collections, institutions, e.g. the digitiser can have access to certain collections they are working on, and not have access to the rest | 3 | In progress | 2024-02-20 |  | 5 |  |  |  |  | Achieved for institution level and collection level in WP5A, post poned the rest, needs testing in keycloak and documentation update needed |  | current status of documentation https://github.com/NHMDenmark/DaSSCo-asset-service/blob/main/documentation/confluence-docs/role-based-access-control.md | keycloak
R3.15 | Provide documentation on the interaction between modules | 3 | In progress | 2024-02-20 |  | 10 |  |  |  |  | We have some diagrams. Still missing various workflows from asset service to file proxy.
R3.16 | Diagram for databases | 3 | In progress | 2024-02-20 |  | 0 |  |  |  |  | Will deploy apache age viewer with proxyauth in front to see database in UI
R3.17 | Provide help/suggestions on automation of scalability | 3 | In progress | 2024-02-20 |  | 4 |  |  |  |  | I think we can do the rest ourselves, if needed, 3-4 hrs of christoffers help will be enough.
R3.18 | Provide results of any stress test or other tests performed to check scalability | 3 | Not started | 2024-02-20 |  | 0
R3.10 | Provide granular control over access at asset level. For example, a curator has read access to all collections. If he wants to collaborate with another curator on his collection, it should be possible for someone else with write access to both, to grant write access to both, the whole collection or even a specific asset only. This is how specify handles access to assets. | 3 | Postponed | 2024-02-20 | [6 empty] | Achieved for institution level and collection level in WP5A, post poned the rest
R3.07 | Fix bugs mentioned on GitHub | 3 | Removed | 2024-02-20 | [6 empty] | On going-inital bugs were fixed
R3.12 - part | Provide delete endpoints on the existing API in production environment. These endpoints should be able to delete institutions, pipelines, workstations, and assets. | 3 | Removed | 2024-02-20 | [5 empty] | 2024-05-15 | Covered by WP1 for assets- we can delete share including the files in the share in fileproxy to clean up space, and also delete files in ERDA is a peculiar way just incase. when deleting a file it doesn't update the delete_file_After_sync: assuming this a way to keep track of all files that existed for an asset but bug in functionality. We are able to delete assets, but |  | The aim is to facilitate automation of integration test and deployment – This is specifically to test if for example a workstation can be created, and then deleted after receiving a confirmation.
R4.01 | External access to a read-only version of the asset is possible for all assets that are not special assets. | 4 |  | 2024-02-20
R4.02 | The default state for all users (without a profile in the IDP) would be no access to special assets. | 4 |  | 2024-02-20
R4.03 | When a user is not logged into the IDP, they would see a log in screen prompting them to log into the IDP for special assets. | 4 |  | 2024-02-20
R4.04 | When a user is logged into the IDP, they cannot see assets they do not have permission for. | 4 |  | 2024-02-20
R4.05 | All links to assets are always to read-only versions of the assets and never to the metadata. | 4 |  | 2024-02-20
R4.06 | With appropriate permissions, an asset should be able to be viewed or downloaded. | 4 |  | 2024-02-20
R4.07 | The ARS metadata field “Restricted Access” should synchronise with the Specify attachment field “Make Public”. | 4 |  | 2024-02-20
R4.08 | Museum staff like a collection manager can grant access to a special asset for an external user to download after they registered on the sign-up page. The collection manager can log in to the ARS for giving the external user access to given special assets after which they automatically will receive an email with a link. (Alternatively, there could be an option for collection managers themselves to send the external user an email with a link). | 4 |  | 2024-02-20
R2A.01 | An asset can consist of both the image and its thumbnail (together they form a single asset) | 2A | In progress | 2024-08-31 |  | 4 | [6 empty] | Needed to decide for how Specify, it was already possible to have multiple files for an asset and on recommendation fo NT it was decided that thumbnails will be part of an asset
R2A.02 | When new assets arrive during the digitisation process into the ARS, use the Specify7 API to insert the necessary records in the Specify database so that the attachments (assets) are accessible from the Specify frontend | 2A | In progress | 2024-02-20 |  | 15 | [6 empty] | To develop a specify adapter that can and crete new attachment record for the existing collection object in specify and add certain metadata from ARS to specify, and Send attachment file from ARS and save in Specify for the newly added attachment record in specify
R2A.03 | Be able to add additional assets to existing records in Specify depending on their association in the ARS. For example, if a new asset of low resolution has been created, it should be added as another attachment (asset) to the existing Specify record. | 2A | In progress | 2024-02-20 |  | 15
R2A.04 | Be able to update existing records in Specify depending on their association in the ARS when they are updated in ARS. For example, if an existing asset has been updated, it should be in the existing Specify record. | 2A | In progress | 2024-02-20 |  | 15
R2A.05 | Keep track of assets that are already in ARS and have a corresponding collection object in Specify, so that they can be added to Specify, automatically. | 2A | In progress | 2024-02-20 |  | 30 |  |  |  |  | Using message queues in the specify adapter which is able to receive new assets, updates for synced assets and then make relevant calls in the Specify API for synchronisation
R2A.06 | There are several installations of Specify and the solution should be incorporated with all of them and is extensible in case for new instances of Specify | 2A | In progress | 2024-02-20 |  | 10
R2A.09 | The Specify Bridge is able to map the metadata fields from ARS to Specify attachment record. | 2A | In progress | 2024-02-20 |  | 20
R2A.07 | Integration Server can query status of this service | 2A | Not started | 2024-02-20 |  | 30
R2A.08 | The Specify bridge is able to serve thumbnails for the assets that have been added in specify frontend when specify request, incase they are not available yet, provide a standard icon? | 2A | Not started | 2024-02-20 |  | 50 |  |  |  |  | This will be revisited when web asset server is replaced, it will become relevant then, because now Specify/webasset server is generating thumbnails
R2B.01 | Be able to create assets in the ARS including metadata when a new attachment record is created in Specify. | 2B |  | 2024-02-20
R2B.01 | It should also be able to attach the attachment (asset) uploaded in Specify to the newly created asset record in the ARS | 2B |  | 2024-02-20
R2B.01 | It should also be able to draw on the linkage between the attachment and specimen records in Specify to populate the ARS metadata. | 2B |  | 2024-02-20
R2B.01 | It should then update the Specify record, such that the asset can be viewed in Specify as well. | 2B |  | 2024-02-20
R2B.01 | Be able to connect the corresponding thumbnail of the attachment to the asset in the ARS. | 2B |  | 2024-02-20
R2B.01 | In case of uploading a new asset to an existing Specify specimen record that already has one or more assets associated with it, the new assets should be related correspondingly inside the ARS. | 2B |  | 2024-02-20
R2B.01 | In case the asset metadata fields that belong in ARS are updated in Specify, they should be synchronised in ARS. | 2B |  | 2024-02-20
R2C.01 | the current Specify web asset server should be completely replaced with the new module, which is fully integrated with Specify and the ARS and any other components of the DaSSCo microarchitecture | 2C |  | 2024-02-20
R2C.02 | The solution must be able to replace the standard web asset server and simulate its current integration with Specify. | 2C |  | 2024-02-20
R2C.03 | It must also be able to exactly simulate and thus replace all functions currently performed by the web asset server, so Specify will continue to operate as normal. | 2C |  | 2024-02-20
R2C.04 | It is flexible and loosely decoupled for providing re-deployment and integration with newer versions of Specify if the inputs and outputs to and from Specify remain the same. | 2C |  | 2024-02-20
R2C.05 | Thumbnails should not be created as separate attachment records in Specify or Assets in ARS. They are part of the asset and should be served on par with the original assets based on the type requested (thumbnail or original). | 2C |  | 2024-02-20
R2C.06 | Web asset server has a security issue where anyone with the url can download a file, this should be plugged when replacing the web asset server with the ARS via Specify bridge | 2C |  | 2024-02-20
R2C.07 | Be able to provide access based on the access rights of the user, meaning normally everyone would have read permission to view assets but in case some assets require permission to view or download, this should be possible | 2C |  | 2024-02-20
R5A.17 | It is possible to get back to list view from the detailed view | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-24
R5A.22 | It should also be possible to select multiple records from the search. | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-24 | Events field shown in search but not populated, could only get it work for "asset_5" |  | Part of add to search functionality
R5A.30 | Searching in the UI should result in a list of assets which are then displayed as a list. | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-06 |  |  | Search functionality
R5A.32 | Tags do not need to be indexed or form a node | 5A | Completed | ?? | [8 empty] | Not sure if this is a requirement
R5A.33 | The assets are visible in the UI in the form of both a list view and detailed view, following querying. | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-06
R5A.34 | The assets from the list view are clickable. Clicking an asset in the list view, will take you to detailed view for that asset. | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-06
R5A.35 | The following fields should be visible in search results view (i.e., summary view): institution, collection, barcode, date_asset_created, file_format | 5A | Completed | 2024-07-10 | [5 empty] | 2024-09-06
R5A.38 | The search performed in the UI can be saved | 5A | Completed | Wasn't requested? | 2024-06-23 |  |  |  |  | 2024-09-24
R5A.41 | There is a landing page for authorised users that has preset defaults and search capabilities and it is straightforward to navigate between different functionalities. | 5A | Completed | 2024-05-23 | 2024-06-23 |  |  |  |  | 2024-09-06
R5A.42 | We do not need to be able to download assets which are in the middle of being processed and have not been synced with ERDA in the ARS UI (as long as we can download the original parent raw version) | 5A | Completed | 2024-07-31 | [8 empty] | Not sure if this a requirement
R5A.01 | Users with write access can edit another user's asset groups (adding and removing assets, deleting the group, adding digitisers, etc.) | 5A | In progress | 2024-08-01 |  | 10 |  |  |  |  | There is no admin role as of yet now, only read/write acccess - decided that. It is not possible to add assets to and existing group.
R5A.02 | After performing a search, in case there are changes made to several fields, there is a confirmation of the action required by the user for that change to be applied. I can either confirm or cancel the change and only after that I can navigate away from that view. | 5A | In progress | 2024-05-23 | 2024-06-23 | 10 |  |  |  |  | Not completely tested, some of the metadata fields are not available like updated user, etc… recently added parent guid when bug was reported |  | To be able to perform correct mistakes or change initial metadata based on new information from UI
R5A.04 | All metadata fields can be viewed in detailed view by all authorised users (read and write access) | 5A | In progress | 2024-05-23 | 2024-06-23 | 5 |  |  |  | 2024-09-06 | Needs more thorough testing - write doesnt work
R5A.06 | Authorised users of the system should be able to search for assets across all fields of the metadata such as various dates, range of dates, one or multiple digitsers, one or many statuses etc. It is possible to combine the search criteria by adding AND/OR/BETWEEN/LIKE/EQUALS/ANY/CONTAINS/STARTSWITH/EMPTY options for the various metadata fields. | 5A | In progress | 2024-05-23 | 2024-06-23 | 15 |  |  |  |  | Provides a programmable way (API) to query the graph database also. currently has a bug- provides incorrect result, see saved search. |  | Search UI for assets in the ARS to perform quality checks etc
R5A.07 | Authorised users with write access have all the functionality with read access, but are also able to edit/add the metadata for an asset selected in the detailed view | 5A | In progress | 2024-05-23 | 2024-06-23 | 15 |  |  |  |  | Not able to do that |  | Basic functionality of how read write works | keycloak
R5A.09 | From detailed view, it is possible to export the metadata as a CSV and also download all the images of the asset. | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  |  | Almost fixed- status from NT |  | Both download the csv as well as the asset with images themselves as seperate functionality
R5A.10 | I am able to list assets edited by another user by searching for a specific metadata field “edited by”. – this is a search capability. | 5A | In progress | 2024-05-23 | 2024-06-23 | 7 |  |  |  |  | Covered as part of the search requirement using metadatafield "updated by". not working. |  | To be able to see latest changes in the system
R5A.11 | In detailed view, it is possible to navigate back and forth through assets that have been retrieved as part of a search. | 5A | In progress | 2024-05-23 | 2024-06-23 | 7 |  |  |  | 2024-09-24 | Needs more thorough testing |  | To see the search result in a sequence for inspection or other purposes
R5A.12A | It is possible to be able to edit/update/add and persist changes to single or multiple records simultaneously with write access [to agreed metadata fields only] | 5A | In progress | 2024-05-23 | 23/06/2024, refined on 10/06/2024 | 7 |  |  |  | 2024-09-24 | Needs more thorough testing |  | Bulk update several record for the ease of correction after audit
R5A.13 | It is possible to create a group of asset records and add to this group with additional records later. | 5A | In progress | 2024-05-23 | 2024-06-23 | 7 |  |  |  | 2024-09-24 | Needs more thorough testing |  | To save search results and maintain/add to them for purpose of correction, bulk action, or similar
R5A.14 | It is possible to download multiple selected assets records returned as a result of a search in the UI, as a CSV, as well as download complete assets as metadata and their corresponding images as an archive | 5A | In progress | 2024-05-23 | 2024-06-23 | 7 |  |  |  | related to R5A.9
R5A.15 | It is possible to download the parent asset and other related assets like derivates of an original asset from detailed view | 5A | In progress | 2024-05-23 | 2024-06-23 | 7 |  |  |  | related to R5A.9 | We are also trying to deploy graph db viewer which might need some expertise but can provide this functionality. This could be dropped. Recently downloading assets not working properly |  | This can be covered by existing search functionality
R5A.16 | It is possible to get an overview, monitor progress, optimize work, and generate reports based on the data from dashboard view | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  |  | Graphs not working properly |  | Part of exisiting functionality
R5A.18 | It is possible to refresh the graphs in dashboard view so that they show the current data, or an auto refresh function can be enabled. | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  |  | Graphs not working properly |  | Changed functionality to provide persisting URLS to share exact graphs and data among ARS users
R5A.19 | It is possible to search for assets without any metadata or assets without any images and so on in the UI | 5A | In progress | 2024-05-23 | 2024-06-23 | 10 |  |  |  |  | Needs more thorough testing - might need a not in the operator field |  | Covererd by search functionality
R5A.21 | It is possible for all users to view and download assets that match a combination of different criteria on various metadata fields. | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  |  | Needs more thorough testing |  | Covered by search functionality
R5A.24 | It should be possible to assign either write or read only access to pre-defined users of ARS, who are able to log in and view records using the UI | 5A | In progress | 2024-05-23 | 2024-06-23 | 5 |  |  |  |  | Based in keycloak. Needs more thorough testing. |  | Allow a limited number of people to use it and try it out (due to lack of may security features most people will have only read access) | keycloak
R5A.25 | It should be possible to download graphs and statistics in the dashboard view as reports and PDFs/editable documents. | 5A | In progress | 2024-05-23 | 2024-06-23 | 5 |  |  |  |  | Graphs not working properly |  | Exisitng functionality, updated to support new features
R5A.26 | It should be possible to edit multiple selected records which result from a search performed in the UI and compare values (or at least summarise the change) before confirming change [to agreed metadata fields only] | 5A | In progress | 2024-05-23 | 23/06/2024, refined on 10/06/2024 | 20 |  |  |  |  | Bulk update works, has quirks like workstation and pipeline are mandatory fields meaning it is not possible to bulk update assets from different work station, pipeline |  | Bulk update- not sure if compare function was postponed?
R5A.29 | It should be possible to view, edit, and download assets in a saved group. | 5A | In progress | 2024-05-23 | 2024-06-23 | 2 |  |  |  |  | Works but needs more thorough testing |  | Went back and forth
R5A.31 | Several assets downloaded at once should be in a structured way, so that they can be shared or audited locally. This requires a simple way to correlate images to the corresponding metadata after downloading as an archive, for example, if metadata is in CSV format, it contains asset name and file names for that asset. | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  | related to R5A.9
R5A.36 | The graphs in the dashboard view in the current version are very sensitive and can go to negative values, instead, the graphs should be adjusted to visualise the data present, and the ranges automatically be set to correspond with the data. | 5A | In progress | 2024-05-23 | 2024-06-23 | 3 |  |  |  |  | Currently has a bug. graphs not working properly |  | Only sensitive in x axis
R5A.39 | The system shows potential values for a field that has an enum list via dropdown but also doesn’t allow to change fields that are system generated. | 5A | In progress | 2024-05-23 | 2024-06-23 | 5 |  |  |  | 2024-09-24 | Missing date for decision. needs more thorough testing |  | Later decides, some fo the fields will be cached, provided a list
R5A.40 | There are default pre-existing dashboard views with statistical information about the project like how many assets digitised in a day over a period of 15 days | 5A | In progress | 2024-05-23 | 2024-06-23 |  |  |  |  | Implemented in a previous WP but not working | Missing date for decision, currently has a bug, detailed in another requirement. | 1 | Satisfied with previous functionality
R5A.23 | It should also record the changes made and persists in the database but also update the relevant fields in the metadata of that asset. | 5A | Removed | 2024-05-23 | 2024-06-23 | [5 empty] | Why was this removed? |  | Basic functionality saving data
R5A.37 | The reports and graphs in dashboard view along with their data are downloadable | 5A | Removed |  |  | 1 |  |  |  |  | Duplicate of R5A.25 |  | Part of existing fucntionality
R5B | It should be possible to search the tags and retrieve the results | 5B | Not started | 2024-05-23 | [6 empty] | Needs more thorough testing |  | Postponed
R5B | It should be possible to view the various related (derivates, original) images of the asset in the detailed view | 5B | Not started | [7 empty] | Needs more thorough testing |  | This could be through clicking on the relevant metadata field?
R5B | All fields in search results in UI can be sorted. If there are multiple barcodes associated with a single asset, it sorts on the first in the list | 5B | Not started | 2024-07-10 | [6 empty] | Delayed to next work package - date for decision missing. was postponed to next iteration -decsion date missing |  | To be able to sort fields to view data in a certain order in the search view
R5B | Authorised users are able to manage users and their access from the UI. Explain what manage users entails. | 5B | Not started | 2024-05-23 | [6 empty] | Delayed to next work package - date for decision missing. needs more thorough testing |  | Admin role, who can create and manage access, like project leader or technical lead to provide access to internal/external users, etc. On request, for now only read and write access can be provided based on access request via keycloak
R5B | Each asset has a thumbnail available which is shown alongside the metadata in the detailed view | 5B | Not started | 2024-05-23 | [6 empty] | postponed - decision date missing |  | View the asset
R5A.43 | It is possible to rollback any edits to records, including bulk updates | 5B |  | not implemented | [8 empty] | Postponed
R5B | It is possible to sort the results of searches in the UI according to different criteria. This criteria could be metadata based or simple ascending, descending order etc. | 5B |  | 2024-05-23 | [6 empty] | You can ascend/descend the institution, collection, barcodes fileformats, created date |  | Postponed
R5B.01 | Provides role-based access to view and edit assets and the metadata status of individual assets. | 5B |  | 2024-02-20 | [6 empty] | Institution and collection implemented in 5A, asset level remaining
R5B.02 | Show failures that occurred while syncing the asset with storage, specify or other similar events, e.g. number of assets that were sent to long-term storage and have been removed from ARS. | 5B |  | 2024-02-20 | [6 empty] | Not directly available on dashboard but available through search
R5B.03 | Provide an interface for performing quality assurance checks on a subset of the images, persist the results, and mark as checked. This will provide project assurance. | 5B |  | 2024-02-20 | [6 empty] | Audited_by fields provides that info but cannot be edited in 5A as of yet and search field for search for audited assets
R5B.04 | Present an overview of the current capacity of the file proxy and the state of assets in use, an overview of the assets that are receiving active updates or are in progress (uploading/downloading). E.g. it could show all the assets in file proxy along with system health to evaluate if the need for adjustments. | 5B |  | 2024-02-20 | [6 empty] | End point available but not in UI
R5B.05 | Enable adjustments of assets in file proxy like removing a lingering asset from file-proxy or assign, or increase/decrease file of different allotted shares. | 5B |  | 2024-02-20
R5B.06 | It should be possible to view images and if the quality of these images is not satisfactory, examine the metadata to compare and look for commonality to figure out the issue (e.g., is it the equipment, digitizer, wrong derivative attached etc.). | 5B |  | 2024-02-20
R5B.07 | It should be possible to give access to a large number of special assets (high-resolution tiff images, CT scans etc.) at the same time to an external user. | 5B |  | 2024-02-20
R5B.08 | It should be possible to assign roles to the functionality and provide a time-based access for certain functionality, for example renaming meta data for several assets, etc. | 5B |  | 2024-02-20
R5B.09 | It is also possible to do user management in the UI. This could be done via IDP KeyCloak and the user should also be able to sign up for the system with basic access and request further access via the system. This might be handled by receiving notifications on assets, users, tagged records, etc | 5B |  | 2024-02-20
R1.02 | Create asset and metadata with only the following information required: institution, collection and GUID | M | In progress | 2023-12-20 |  | 8 |  |  |  |  | Has issues like needs asset pid to create metadata |  | From previous version, not detailed here
| Be able to see all the open shares in the file proxy - i.e., the precise status list shown. See notes for R1.14. | M | In progress |  |  | 10
| Ensure that status is a required piece of data for creating a new asset and its metadata (addition to requirement R1.2) | M | In progress |  |  | 8
| When a derivative asset needs to be created in the ARS, the parent GUID should be filled in (as sent by integration server) for both jpegs and tifs | M | In progress |  |  | 20
R3.19 | Provide granular control over access at institution and collection level. |  | In progress | 2024-05-30 | [6 empty] | Documentation of this is missing |  |  | keycloak
R3.20 | Deploy test suite |  | Not started | need to agree |  | 10 | 1

## Pivot
Row Labels | Sum of NT Hours Predicted
1 | 78
Completed
In progress | 78
3 | 306
Completed
In progress | 306
Removed
4
(blank)
2A | 189
In progress | 109
Not started | 80
2B
(blank)
2C
(blank)
5A | 163
Completed
(blank)
In progress | 163
Removed
Not started
5B
(blank)
M | 46
In progress | 46
Grand Total | 782

## Values
Completed
In progress
Not started
Removed
Postponed

## date wise comm with NT
emails with chrisotffer
communication with Pip - summarising date wise communication with NT on WP 5A
delivered to christoffer in hand - as source of the 23rd May document
2024-05-13 | 2024-06-06 | between pip and me - 26/06/2024
You can get started by introducing the search capability for all metadata fields in the UI. | The UI is fine as it is now - specifically showing graphs per Specimen and not assets. | Summary of the UI demo meeting with NorthTech on 10th June 2024
It should also be possible to select specific values, like dates or barcodes but also a range of values like in the last 40 days. | Auto refresh is not needed and the refresh button is fine. | End point: make available the endpoints for search so that we can also do it programmatically – solution – swagger should have everything
It should also be able to combine several fields like in Institution NHMD AND/OR AU, Collection Pinned Insects find all barcodes starting from 10002344 to 10002389 | Pip wants to play with zoom functionality in graphs, so please don’t remove it for now. | Swagger docs have been updated – documentation on how to access the API – found some issues- needs to follow up
| Reports in PDF and data in CSV format are fine, don’t need reports in editable format. | List of metadata fields that we need for bulk updates – especially tags (what happens to existing tags)
Bulk Update | The requirement 28,29,30 were excluded as | File proxy: get info about disk size from the Operating system – there were some issues where disk size was coming from a file instead it needs to be dynamic.
It should then be possible to edit a particular for all the records in the search. | In 28 is almost implemented and only per digitizer is not there, and that is fine, digitizer is not needed. | Add and & or blocks at the node level of the search engine
I would also like to get an estimate on the most simplistic time-constrained rollback in case the records have not been further changed. | 29 and 30 can be covered with saved searches. | Columns in search engine (selectable)– next version
I would also like an estimate on granulaity of role based access. I mean how much of difference is fi we go for Institution, collection vs Institution, Collection, Specimen, assets also where roles can be added by us as the need arises in the future. | So basically, all requirements are covered. Pip said and I concur that it would be nice to have them in the document for posterity with a side note, like covered through saved search functionality or already done in the previous version, so please add it in the document and send the updated version with the estimate mail. | Pagination for search results
The drop-down list for Enum lists of metadata in the search UI
Have a refresh button to make sure you viewing the latest metadata.
| handed christoffer in per at meeting end of may | Case insensitive search toggle?
| Requirements for UI v1 (initial essential only) 2024_04_22 | # GitHub 49 UI and detailed view UI – discussed with Pip and gave feedback to NorthTech
Want to keep the zoom in the graph – still there but now only on x axis – disabled for y axis
1. As a minimum there should be two user roles for access to the ARS via the UI: read only and write access (at the beginning)
2. When a user logs in to the UI, there should be an obvious way to go to the search screen
| 3. The search screen should show all of the metadata fields with a search box by each | Follow-up meetings with NorthTech and decisions 17th June 2024
4. Adding values to multiple fields in the search screen performs an AND search
| 5. It is possible to search for ranges (e.g., a range of dates or barcode numbers) | Decided on work package based status updates
| 6. Searching will return a list of assets | For bulk updates: list of metadata fields that can be bulk updated are now decided to be only where the metadata fields are not a list.
| 7. The number of assets retrieved by a search will be displayed | This is because the way bulk update works is that it just replaces the existing data, so if there is already data in the list, it will then just be replaced – reason is that it is much more involved bulk update with take more time, and for now it can be consider as the first version.
| 8. It is possible to configure what fields can be seen in list view | Bulkt update will not work for asset guid and specimen pid either
| 9. It should be possible to sort the list of assets retrieved by any of the metadata fields | Tags field is exception which is a list field but it will then show the existing tags and in case of bulk update it will ask if it is to be added or replace d for the existing list.
| 10. Searching should be fast | Graphs have custom ranges and scrollable on only x-axis
| 11. It should be possible to select multiple assets from the list view using a check box beside each entry | You can share links of the graphs with custom date ranges so others will have the same view of the graph as you.
12. It should be possible to export asset metadata from selected records as a csv
| 13. It should be possible to download a group of selected assets | 25th June status meeting
14. Downloading assets should be reasonable quick and easy
| 15. It should be possible to create groups of asset records and to add to that group with additional records at a later date, and to view and edit records in the group. | Thomas is working on roles based read& write access on institution and collections
| 16. It should be possible to name/rename asset groups | Found a bug where collection names need to unique across institutions otherwise it cannot find out which collection – will fix this
| 17. It should be possible to see full metadata of asset records in a detailed view (showing all metadata fields) | Nicolas worked on bulk update and test suite and will demo it on Friday the 5 th of July – @you wanna attend?
| 18. Detailed view should be accessible from list view either by double clicking on the asset record or selecting it from a menu or ribbon | Thomas will also demo the read and write access on institutions and collections
| 19. It should be possible to navigate (forward, back, first and last arrows) through records in detailed view | Matilde might also demo something – she was on holiday so don’t know status of search UI
20. In detailed view, there should be a thumbnail of the asset in the record (CAN BE PUSHED TO LATER?)
21. In detailed view, it should be possible to get a larger view of an asset by double clicking on the thumbnail picture (CAN BE PUSHED TO LATER)
| 22. There should be an option to download the asset and/or asset record (as csv) in detailed view. | Estimates
| 23. It should be possible to search for asset records edited by another user | WK5A – 150 this month - almost reached around half of the estimate for UI reprioritized work package
| 24. It should be possible to add data to metadata fields (except the system generated ones) in detailed view (e.g., correcting name of digitiser) | The 150 hrs from previous month from Matilde is actually a mix of both Nikolas and Matilde’s work as Nikolas doesn’t have emagine id
| 25. It should be possible to bulk update metadata of multiple asset records at once | So Nikolas worked on the test suite and swagger documentation in that month which is not part of WK5A approx. I know 85 hrs approx. were for test suite and some hrs were for swagger doc
| 26. It should not be possible to navigate away from a record if changes have been made without either saving the changes or cancelling them | By the way I will add this to the table of work package hrs
27. As someone with edit access to the ARS, it should be possible to add other people so they can access the ARS via the UI
28. It should be possible to see how rates have changed over time/per digitizer/per pipeline etc. I should be able to see this graphically (and export the graphs), but also capture statistics that I can use in reports. This will allow me to monitor progress, manage and optimize work as well as report on it.
29. It should be possible to find out how many images and what type (e.g., tif, jpeg) have been uploaded in the last year.
30. It should be easy to find the average number of images per specimen for any particular pipeline, workstation, collection, prep type or institution
31. The graphical display of rates should not be too sensitive, so that it is easy to use and manipulate.
32. The graphical display of rates should not show minus figures
33. It should be easy to refresh the graphical display of rates, the health and stats and to ensure that they are refreshed regularly automatically
34. It should be able to investigate specimens that have no images attached or vice versa