## Overview
Status of DaSSCo Asset Registry System Phase 3 work
Work package | Status | Progress | Start | End | Original Estimate | Latest Estimate | Hours actual (billed)
1A | Complete | 100% | 2023-12-01 | 2024-02-29 |  | 239.5 | 239.5
1B | Partially complete | 86.52% | 2024-03-01 | (31/08/2024) | 118 | 282 | 244
2A | Partially complete | 63.71% | 2024-06-27 | (31/08/2024) | 506 | 520.75 | 331.75
2B | Not started | #DIV/0! |  |  | 0 | 0 | 0
2C | Not started | #DIV/0! |  |  | 0 | 0 | 0
3 | Partially complete | 59.73% | 2024-04-01 | (31/06/2024) | 289 | 221 | 132
4 | Not started | #DIV/0! |  |  | 456 | 0 | 0
5A | Partially complete | 83.2% | 2024-05-13 | (31/08/2024) | 530 | 970 | 807
5B | Not started | #DIV/0! |  |  | 0 | 0 | 0
Misc | [5 empty] | 74.45 | 28.45
TOTAL |  | #DIV/0! | 2023-12-01 | 2025-06-30 | 1899 | 1993.75 | 1543.2
HOURS | Current spend % | 81.2638 |  | COST | Current spend % | 75.9076
| Allowed overspend % | 110 |  |  | Allowed overspend % | 110 | 2420000
| Projected overspend % | 104.9895 |  |  | Projected overspend % | 97.5095
[5 empty] | Projected overspend DKK | -54790.7372
[5 empty] | Projected overspend above allowed DKK | -274790.7372

## Hours by package
Month | WP 1A | WP 1B | WP 2A | WP 2B | WP 2C | WP 3 | WP 4 | WP 5A | WP 5B | WP M |  | TOTAL | INVOICE TOTALS | Total for SKI 3
2023/12 | 25 | [10 empty] | 25 | 25
2024/01 | 92.5 | [10 empty] | 92.5 | 92.5
2024/02 | 122 | [10 empty] | 122 | 122
2024/03 |  | 54.5 | [7 empty] | 12 |  | 66.5 | 66.5 | 66.5
2024/04 |  | 31 |  |  |  | 88 |  |  |  | 16.45 |  | 135.45 | 135.45 | 135.45
2024/05 |  | 40 |  |  |  | 7 |  | 180 |  |  |  | 227 | 227 | 227
2024/06 |  | 68.5 | 42.75 |  |  | 20 |  | 187.5 |  |  |  | 318.75 | 318.75 | 318.75
2024/07 |  |  | 51.5 |  |  |  |  | 369.5 |  |  |  | 421 | 421 | 421
2024/08 |  | 50 | 213 |  |  |  |  | 47.5 |  |  |  | 310.5 | 310.5 | 310.5
2024/09 |  | 11.5 | 24.5 |  |  | 17 |  | 22.5 |  |  |  | 75.5 | 75.5 | 75.5
2024/10 | [9 empty] | 28.5 |  | 28.5 | 28.5 | 28.5
2024/11 | [11 empty] | 0 |  | 0
2024/12 | [11 empty] | 0 |  | 0
2025/01 | [11 empty] | 0 |  | 0
2025/02 | [11 empty] | 0 |  | 0
2025/03 | [11 empty] | 0 |  | 0
2025/04 | [11 empty] | 0 |  | 0
2025/05 | [11 empty] | 0 |  | 0
2025/06 | [11 empty] | 0 |  | 0
2025/07 | [11 empty] | 0 |  | 0
2025/08 | [11 empty] | 0 |  | 0
2025/09 | [11 empty] | 0 |  | 0
2025/10 | [11 empty] | 0 |  | 0
2025/11 | [11 empty] | 0 |  | 0
TOTAL | 239.5 | 244 | 331.75 |  |  | 132 | 0 | 807 | 0 | 28.45 | 0 | 1794.2 | 1718.7 | 1479.2

## Hours by consultant
Month | TSB | MB | CGH | NJJ |  |  | TOTAL | INVOICE TOTAL
2024/03 | 35.5 | 12 | 19 | 0 |  |  | 66.5 | 66.5
2024/04 | 31 | 16.45 | 88 | 0 |  |  | 135.45 | 135.45
2024/05 | 50 | 153 | 24 | 0 |  |  | 227 | 227
2024/06 | 98.5 | 187.5 | 32.75 | 0 |  |  | 318.75 | 318.75
2024/07 | 101.5 | 298.5 | 21 | 0 |  |  | 421 | 421
2024/08 | 75 | 78 | 0 | 157.5 |  |  | 310.5 | 310.5
2024/09 | 11.5 | 7.5 | 17 | 39.5 |  |  | 75.5
2024/10 | 18.5 | 0 | 10 | 0 |  |  | 28.5 | 28.5
2024/11 | [6 empty] | 0
2024/12 | [6 empty] | 0
2025/01 | [6 empty] | 0
2025/02 | [6 empty] | 0
2025/03 | [6 empty] | 0
2025/04 | [6 empty] | 0
2025/05 | [6 empty] | 0
2025/06 | [6 empty] | 0
2025/07 | [6 empty] | 0
2025/08 | [6 empty] | 0
2025/09 | [6 empty] | 0
2025/10 | [6 empty] | 0
2025/11 | [6 empty] | 0
TOTAL | 421.5 | 752.95 | 211.75 | 197 | 0 | 0 | 1583.2 | 1507.7

## Cost
Month | TSB | MB | CGH | NJJ |  |  | TOTAL | INVOICE TOTAL
2024/03 | 40796.6 | 11287.2 | 26205.75 | 0 |  |  | 78289.55 | 78289.55
2024/04 | 35625.2 | 15472.87 | 121374 | 0 |  |  | 172472.07 | 172472.07
2024/05 | 57460 | 143911.8 | 33102 | 0 |  |  | 234473.8 | 234473.8
2024/06 | 113196.2 | 176362.5 | 45170.44 | 0 |  |  | 334729.14 | 334729.14
2024/07 | 116643.8 | 280769.1 | 28964.25 | 0 |  |  | 426377.15 | 426377.15
2024/08 | 86190 | 73366.8 | 0 | 148144.5 |  |  | 307701.3 | 307701.3
2024/09 | 13215.8 | 7054.5 | 23447.25 | 37153.7 |  |  | 80871.25 | 80871.25
2024/10 | 21260.2 | 0 | 13792.5 | 0 |  |  | 35052.7 | 35052.7
2024/11 | [6 empty] | 0
2024/12 | [6 empty] | 0
2025/01 | [6 empty] | 0
2025/02 | [6 empty] | 0
2025/03 | [6 empty] | 0
2025/04 | [6 empty] | 0
2025/05 | [6 empty] | 0
2025/06 | [6 empty] | 0
2025/07 | [6 empty] | 0
2025/08 | [6 empty] | 0
2025/09 | [6 empty] | 0
2025/10 | [6 empty] | 0
2025/11 | [6 empty] | 0
TOTAL | 484387.8 | 708224.77 | 292056.19 | 185298.2 | 0 | 0 | 1669966.96 | 1669966.96

## Sheet1
Northtech Consultant Hours for: October 2024
Consultant | Hours | WP1 | WP2A | WP2B | WP2C | WP3 | WP4 | WP5A | WP5B
CGH | 10
MB | 0
TSB | 18.5
NJJ | 0