## Overview
Status of DaSSCo Asset Registry System Phase 3 work
Work package | Status | Progress | Start | End | Original Estimate | Latest Estimate | Hours actual (billed) | Remaining
1A | Complete | 100% | 2023-12-01 | 2024-02-29 |  | 239.5 | 239.5 | 0
1B | Partially complete | 92.78% | 2024-03-01 | (31/08/2024) | 118 | 263 | 244 | 19
2A | Partially complete | 63.1% | 2024-06-27 | (31/08/2024) | 506 | 525.75 | 331.75 | 194
2B | Not started | #DIV/0! |  |  | 0 | 0 | 0 | 0
2C | Not started | #DIV/0! |  |  | 0 | 0 | 0 | 0
3 | Partially complete | 61.11% | 2024-04-01 | (31/06/2024) | 289 | 216 | 132 | 84
4 | Not started | #DIV/0! |  |  | 456 | 0 | 0 | 0
5A | Partially complete | 82.85% | 2024-05-13 | (31/08/2024) | 530 | 974 | 807 | 167
5B | Not started | #DIV/0! |  |  | 0 | 0 | 0 | 0
Misc | [5 empty] | 74.45 | 28.45 | 46
TOTAL |  | 74.96% | 2023-12-01 | 2025-06-30 | 1899 | 1978.75 | 1543.2 | 435.55
HOURS | Current spend % | 81.2638 |  | COST | Current spend % | 80.2276
| Allowed overspend % | 110 |  |  | Allowed overspend % | 110 | 2420000
| Projected overspend % | 104.1996 |  |  | Projected overspend % | 101.2246
[5 empty] | Projected overspend DKK | 26940.6845
[5 empty] | Projected overspend above allowed DKK | -193059.3155

## Hours by package
Month | WP 1A | WP 1B | WP 2A | WP 2B | WP 2C | WP 3 | WP 4 | WP 5A | WP 5B | WP M |  | TOTAL | INVOICE TOTALS | Total for SKI 3
2023/12 | 25 | [10 empty] | 25 | 25
2024/01 | 92.5 | [10 empty] | 92.5 | 92.5
2024/02 | 122 | [10 empty] | 122 | 122
2024/03 |  | 54.5 | [7 empty] | 12 |  | 66.5 | 66.5 | 66.5
2024/04 |  | 31 |  |  |  | 88 |  |  |  | 16.45 |  | 135.45 | 135.45 | 135.45
2024/05 |  | 40 |  |  |  | 7 |  | 180 |  |  |  | 227 | 227 | 227
2024/06 |  | 68.5 | 42.75 |  |  | 20 |  | 187.5 |  |  |  | 318.75 | 318.75 | 318.75
2024/07 |  |  | 51.5 |  |  |  |  | 369.5 |  |  |  | 421 | 421 | 421
2024/08 |  | 50 | 213 |  |  |  |  | 47.5 |  |  |  | 310.5 | 310.5 | 310.5
2024/09 |  | 11.5 | 24.5 |  |  | 17 |  | 22.5 |  |  |  | 75.5 | 75.5 | 75.5
2024/10 | [9 empty] | 28.5 |  | 28.5 | 28.5 | 28.5
2024/11 | 36.25 | [6 empty] | 36.25 |  | 8.5 |  | 81 | 81 | 81
2024/12 | [11 empty] | 0 |  | 0
2025/01 | [11 empty] | 0 |  | 0
2025/02 | [11 empty] | 0 |  | 0
2025/03 | [11 empty] | 0 |  | 0
2025/04 | [11 empty] | 0 |  | 0
2025/05 | [11 empty] | 0 |  | 0
2025/06 | [11 empty] | 0 |  | 0
2025/07 | [11 empty] | 0 |  | 0
2025/08 | [11 empty] | 0 |  | 0
2025/09 | [11 empty] | 0 |  | 0
2025/10 | [11 empty] | 0 |  | 0
2025/11 | [11 empty] | 0 |  | 0
TOTAL | 239.5 | 244 | 331.75 |  |  | 132 | 0 | 807 | 0 | 28.45 | 0 | 1794.2 | 1718.7 | 1479.2

## Hours by consultant
Month | TSB | MB | CGH | NJJ |  |  | TOTAL | INVOICE TOTAL
2024/03 | 35.5 | 12 | 19 | 0 |  |  | 66.5 | 66.5
2024/04 | 31 | 16.45 | 88 | 0 |  |  | 135.45 | 135.45
2024/05 | 50 | 153 | 24 | 0 |  |  | 227 | 227
2024/06 | 98.5 | 187.5 | 32.75 | 0 |  |  | 318.75 | 318.75
2024/07 | 101.5 | 298.5 | 21 | 0 |  |  | 421 | 421
2024/08 | 75 | 78 | 0 | 157.5 |  |  | 310.5 | 310.5
2024/09 | 11.5 | 7.5 | 17 | 39.5 |  |  | 75.5
2024/10 | 18.5 | 0 | 10 | 0 |  |  | 28.5 | 28.5
2024/11 | 72.5 |  | 8.5 |  |  |  | 81 | 81
2024/12 | [6 empty] | 0
2025/01 | [6 empty] | 0
2025/02 | [6 empty] | 0
2025/03 | [6 empty] | 0
2025/04 | [6 empty] | 0
2025/05 | [6 empty] | 0
2025/06 | [6 empty] | 0
2025/07 | [6 empty] | 0
2025/08 | [6 empty] | 0
2025/09 | [6 empty] | 0
2025/10 | [6 empty] | 0
2025/11 | [6 empty] | 0
TOTAL | 494 | 752.95 | 220.25 | 197 | 0 | 0 | 1664.2 | 1588.7

## Cost
Month | TSB | MB | CGH | NJJ |  |  | TOTAL | INVOICE TOTAL
2024/03 | 40796.6 | 11287.2 | 26205.75 | 0 |  |  | 78289.55 | 78289.55
2024/04 | 35625.2 | 15472.87 | 121374 | 0 |  |  | 172472.07 | 172472.07
2024/05 | 57460 | 143911.8 | 33102 | 0 |  |  | 234473.8 | 234473.8
2024/06 | 113196.2 | 176362.5 | 45170.44 | 0 |  |  | 334729.14 | 334729.14
2024/07 | 116643.8 | 280769.1 | 28964.25 | 0 |  |  | 426377.15 | 426377.15
2024/08 | 86190 | 73366.8 | 0 | 148144.5 |  |  | 307701.3 | 307701.3
2024/09 | 13215.8 | 7054.5 | 23447.25 | 37153.7 |  |  | 80871.25 | 80871.25
2024/10 | 21260.2 | 0 | 13792.5 | 0 |  |  | 35052.7 | 35052.7
2024/11 | 83317 | 0 | 11723.63 | 0 |  |  | 95040.63 | 95040.63
2024/12 | [6 empty] | 0
2025/01 | [6 empty] | 0
2025/02 | [6 empty] | 0
2025/03 | [6 empty] | 0
2025/04 | [6 empty] | 0
2025/05 | [6 empty] | 0
2025/06 | [6 empty] | 0
2025/07 | [6 empty] | 0
2025/08 | [6 empty] | 0
2025/09 | [6 empty] | 0
2025/10 | [6 empty] | 0
2025/11 | [6 empty] | 0
TOTAL | 567704.8 | 708224.77 | 303779.82 | 185298.2 | 0 | 0 | 1765007.59 | 1765007.59

## Sheet1
Northtech Consultant Hours for: October 2024
Consultant | Hours | WP1 | WP2A | WP2B | WP2C | WP3 | WP4 | WP5A | WP5B
CGH | 10
MB | 0
TSB | 18.5
NJJ | 0