## Master
# | Description | Version | Status | Approved Date | Hours Predicted | Priority | Github ticket | Completed Date | Notes
| A digitizer with account in keycloak should be able login to ingestion client. | V2 | Completed | Not yet approved
| A digitizer must ble able to then select the directory and process assets from that directory. | V2 | Completed | Not yet approved
| Delete files from TUSD, temporary folder on server | V2 | Completed | Not yet approved
| The client has a better user interface. | V2 | Completed | Not yet approved
| Integrity metrics and checks | V2 | Completed | Not yet approved
| The system should be broken into microservices to assign different responsibilities. | V2 | Completed | Not yet approved
| Redesign and deploy Utils package to PyPi, updated to conform to new metadata | V2 | Completed | Not yet approved
| The IC should be able to verify if each TIF has a corresponding raw file and save the original names in a db | V2 | Not started | Not yet approved | 15 | 1
| automatically fetch the values from db based on Workstation | V2 | Not started | Not yet approved | 5 | 1
| Deploy and distrube distribute Ingestion Client | V2 | Not started | Not yet approved | 10 | 1
| Documentation | V2 | Not started | Not yet approved | 45 | 1
| Testing | V2 | Not started | Not yet approved | 30 | 1
| Push everything to github | V2 | Not started | Not yet approved | 5 | 1
| Autoupdate the IC application | V2 | Not started | Not yet approved | 15 | 2
| Delete files from workstation | V2 | Not started | Not yet approved | 5 | 1
| Error tracking/logging | V2 | Not started | Not yet approved | 50
| The digitiser is presented with the metadata fields with the options to select values for those fields | V2 | Not started | Not yet approved
| The digitiser can save the metadata fields, these fields should apply to all files in working directory | V2 | Not started | Not yet approved
| Digitser is able to the start processing which queues the data to the server and processses any incoming requests | V2 | Not started | Not yet approved
| Continuous file upload. | V3 | Not started | Not yet approved | 50 | 4
| Role-based access control for user management | V3 | Not started | Not yet approved | 25
| Role based access control selecting metadata field | V3 | Not started | Not yet approved | 25
| Role based access for institutions and Pipelines with different work flows | V3 | Not started | Not yet approved | 40
| The server consumes a message containing an HTTP link to upload to ARS | V3 | Not started | Not yet approved | 50
| Error handling if ARS is down | V3 | Not started | Not yet approved | 30
| The architecture should include a health check microservice that monitors individual services. It notifies the other services when a specific service is currently down. | V3 | Not started | Not yet approved | 60
| Create different pipelines for AU & Decouple Species Web & OCR to Ingestion Client. | V3 | Not started | Not yet approved | 125
| Create different pipelines for DTU | V3 | Not started | Not yet approved | 1000
| Adjust folder structure and work flows & metadata for seperate pipelines | V3 | Not started | Not yet approved
| Add automation for deleting |  | Not started | Not yet approved | 4 | 1
| Data export to CSV |  | Not started | Not yet approved | 60
| Include Barcode in data send to species/db, Aksel already reads the barcode |  | Not started | Not yet approved | 15

## Values
Completed
In progress
Not started
Removed
Postponed

## Original
| Ingestion Client | Version 1 |  | Khaled hrs left: 45 approx
| Work Package Overview | Keycloak integration for loging in, Stable file transfer, better UI
# | Requirements | Estimate in Hrs | Priority | Status | Version
| A digitizer with account in keycloak should be able login to ingestion client. |  |  | done | V1
| A digitizer must ble able to then select the directory and process assets from that directory. |  |  | done | V1
| The IC should be able to verify if each TIF has a corresponding raw file and save the original names in a db | 15 | 1 | not done | V1
| The digitiser is presented with the metadata fields with the options to select values for those fields |  |  |  | V1
| automatically fetch the values from db based on Workstation | 5 | 1 | not done | V1
| The digitiser can save the metadata fields, these fields should apply to all files in working directory |  |  |  | V1
| Digitser is able to the start processing which queues the data to the server and processses any incoming requests |  |  |  | V1
| autoupdate the IC application | 15 | 2 | not done | V1
| Delete files from workstation | 5 |  | not done | V1
| Delete files from TUSD, temporary folder on server |  |  | done | V1
| The client has a better user interface. |  |  | done | V1
| Integrity metrics and checks |  |  | done | V1
| Error tracking/logging | 50 |  | not done | V1
| The system should be broken into microservices to assign different responsibilities. |  |  | done | V1
| Redesign and deploy Utils package to PyPi, updated to conform to new metadata |  |  | done | V1
| Deploy and distrube distribute Ingestion Client | 10 | 1 | not done | V1
| Documentation | 45 | 1 | not done | V1
| Testing | 30 | 1 | not done | V1 | hrs are approx for khaled
| Push everything to github | 5 | 1 | not done | V1
Version 2 | coordination with Integration server, integration of AU and DTU pipelines, Role based access, error handling, health service
| Role-based access control for user management | 25 |  | not done | V2
| Role based access control selecting metadata field | 25 |  | not done | V2
| Role based access for institutions and Pipelines with different work flows | 40 |  | not done | V2
| The server consumes a message containing an HTTP link to upload to ARS | 50 |  | not done | V2
| Error handling if ARS is down | 30 |  | not done | V2
| Continuous file upload. | 50 | 4 | not done | V2
| The architecture should include a health check microservice that monitors individual services. It notifies the other services when a specific service is currently down. | 60 |  | not done | V2
| Create different pipelines for AU & Decouple Species Web & OCR to Ingestion Client. | 125 |  | not done | V2
| Create different pipelines for DTU | 1000 |  | not done | V2
| Adjust folder structure and work flows & metadata for seperate pipelines |  |  | not done | V2
Current AU adjustments
| Add automation for deleting | 4 | 1 | not done
| Data export to CSV | 60 |  | not done
| Include Barcode in data send to species/db, Aksel already reads the barcode | 15 |  | not done